## Product Backlog
ID | User Story | Priority | Story Points | Sprint | Assignee(s) | Status | Acceptance Criteria
US-01 | As a farmer, I want to register and login so I can sell my products. | High | 5 | Sprint 1 | Shuri, Bruce Banner | To Do | Auth pages exist, custom user model separates Farmer/Buyer.
US-02 | As a buyer, I want to register and login so I can purchase crops. | High | 3 | Sprint 1 | Shuri, Bruce Banner | To Do | Buyer role can access catalog but not dashboard.
US-03 | As a DevOps lead, I want to setup CI/CD on Render so code deploys automatically. | High | 5 | Sprint 1 | Falcon, Captain America | To Do | GitHub push to main triggers Render build. DB is Neon Postgres.
US-04 | As a farmer, I want to add, edit, and delete my crop listings with images. | High | 8 | Sprint 2 | Bruce Banner, Shuri | To Do | CRUD operations work, images upload to storage.
US-05 | As a buyer, I want to view a catalog of crops with search and filters. | High | 5 | Sprint 2 | Spider-Man, Black Widow | To Do | Catalog page displays grid of products with working search bar.
US-06 | As a buyer, I want to add items to a cart and checkout (simulated). | High | 8 | Sprint 2 | Shuri, Spider-Man | To Do | Cart persists in session/DB, checkout generates an Order record.
US-07 | As a farmer, I want to see a localized weather widget to plan harvests. | Medium | 3 | Sprint 3 | Black Widow, Tony Stark | To Do | Weather API integrated and displayed on dashboard.
US-08 | As a farmer, I want crop recommendations based on location and season. | High | 13 | Sprint 3 | Tony Stark, Bruce Banner | To Do | Recommendation engine outputs suggested crops based on inputs.
US-09 | As a farmer, I want an insights dashboard showing my sales trends. | Medium | 8 | Sprint 3 | Black Widow, Doctor Strange | To Do | Chart.js displays sales volume over time.
US-10 | As a buyer, I want to track my order status (Pending/Shipped/Delivered). | Low | 3 | Sprint 4 | Spider-Man, Hawkeye | To Do | Order history page shows current status.

## Sprint 1 Plan
Task ID | Task Description | Parent Story | Assignee(s) | Est. Hours | Status
T-1.1 | Initialize Django project & Neon DB | Infrastructure | Bruce Banner, Falcon | 6 | Not Started
T-1.2 | Setup Render hosting and GitHub Actions | US-03 | Falcon, Tony Stark | 8 | Not Started
T-1.3 | Create Custom User Model (Farmer/Buyer) | US-01, US-02 | Shuri, Bruce Banner | 12 | Not Started
T-1.4 | Design initial Tailwind Templates & UI components | UI/UX | Doctor Strange, Spider-Man, Black Widow | 15 | Not Started
T-1.5 | Write baseline test cases for Auth & CI pipelines | QA | Scarlet Witch, Hawkeye | 8 | Not Started

## Burndown Data
Day | Ideal Remaining Points | Actual Remaining Points
Sprint 1 - Day 0 | 25 | 25
Sprint 1 - Day 1 | 21 | 25
Sprint 1 - Day 2 | 18 | 20
Sprint 1 - Day 3 | 14 | 15
Sprint 1 - Day 4 | 10 | 10
Sprint 1 - Day 5 | 7 | 8
Sprint 1 - Day 6 | 3 | 4
Sprint 1 - Day 7 | 0 | 0